## Overview
Vertex Frontier ¦ Parquet-to-Iceberg Migration Control Pack
A practical workbook for preflight, procedure selection, validation, cutover, ownership, and rollback decisions.
How to use this workbook
Complete the tabs from left to right. Do not mark a table Go until the source state, schema, partition mapping, ownership, validation evidence, and rollback path are recorded. This workbook is a decision and evidence template; it does not replace testing in your actual engine and catalog versions.
Workbook map
Tab | Purpose | Completion rule
Preflight | Dataset classification, schema and ownership gates | Complete before running a migration procedure.
Procedure Matrix | Choose migrate, snapshot, add_files, or rewrite | Use the evidence column to justify the choice.
Validation | Record partition, aggregate, null, duplicate, and query checks | Attach query outputs or checksums in the evidence field.
Cutover | Compare freeze-and-switch, dual-write, blue/green, and shadow | Select one primary pattern and define rollback.
Risk Register | Track red flags and Go/Hold/Rollback decisions | Keep the record with the migration audit trail.
Core operating rule
Migration is complete only when table identity, writer ownership, cleanup authority, validation evidence, and rollback behavior are explicit. A successful metadata commit is one event—not the acceptance criterion.
Prepared by Vertex Frontier
Pattern | Downtime score
Freeze-and-switch | 1
Dual-write | 1
Blue/green | 1
Shadow rewrite | 3

## Preflight
Preflight Gate
Classify the source estate and collect evidence before selecting a migration procedure.
Dataset classification
Code | Observed state | Evidence | Initial implication | Status
State A | Hive-registered Parquet | Catalog definition, schema, partitions, and location are discoverable. | Snapshot or migrate may fit after writer and catalog checks. | Not started
State B | Raw Hive-style Parquet | Paths encode values such as event_date=YYYY-MM-DD. | Define and validate a source table before adoption. | Not started
State C | Raw non-Hive-partitioned Parquet | Partition values are not reliably encoded in paths. | Prefer explicit mapping or rewrite; hold add_files until proven safe. | Not started
State D | Mixed or dirty dataset | Multiple schemas, writers, layouts, or ownership boundaries. | Rewrite or stage only after normalizing the contract. | Not started
Preflight evidence checklist
Gate | Acceptance evidence | Evidence link / note | Status
Schema inventory | Every distinct writer/partition family profiled |  | Open
Field identity | Field IDs, name fallback, renames, duplicate names checked |  | Open
Type compatibility | Numeric, timestamp, decimal, nullability changes reviewed |  | Open
Partition mapping | Path columns, file columns, missing and inconsistent paths checked |  | Open
Writer inventory | Batch, streaming, crawler, notebook, and repair jobs listed |  | Open
Reader inventory | Catalog readers and direct path readers listed |  | Open
Ownership | Write, delete, lifecycle, compaction, and catalog permissions mapped |  | Open
Rollback | Source backup or prior snapshot and observation window defined |  | Open

## Procedure Matrix
Procedure Decision Matrix
Select a path based on source state, isolation, writer control, and layout quality.
Decision table
Path | What changes | Use when | Do not choose first when | Primary risk | Decision note | Status
Snapshot | New Iceberg table; source remains available | Source must stay queryable during test or staged cutover | Source can change without synchronization plan | Target drifts from source changes |  | Candidate
Migrate | Iceberg table replaces source identity | Writers can stop; catalog supports replacement | Legacy writers cannot stop or catalog limitation applies | Writer/reader breaks or unsafe replacement |  | Candidate
add_files | Known files registered into existing Iceberg table | Schema, partition mapping, and duplicate checks are proven | Dataset state or ownership is unclear | Wrong partitions or duplicate rows |  | Candidate
Full rewrite / shadow | New physical data and metadata | Need isolation, cleanup, deduplication, new partitioning, or better file sizing | No compute/storage window and no staging path | Higher cost and reconciliation burden |  | Candidate
Selected execution record
Field | Value | Evidence / note
Source table / path
Target catalog / table
Iceberg version / engine version
Selected path
Idempotency key
Planned operator / approver
Rollback trigger

## Validation
Validation Scorecard
Record comparison results before moving readers or writers to the Iceberg table.
Validation checks
Check | Comparison | Pass rule | Evidence link / query | Status
File coverage | Expected source files versus Iceberg-referenced files | No unexplained missing, duplicate, or out-of-scope file |  | Open
Partition counts | Counts by every important partition | No unexplained mismatch |  | Open
Aggregates | Sums, min/max, and distinct counts for business measures | No unexpected drift or coercion |  | Open
Null rates | Keys, partitions, and frequently filtered columns | No unexpected increase |  | Open
Duplicate keys | Business key or event ID counts | No duplicates introduced by overlap or re-registration |  | Open
Query diffs | Representative production queries and checksums | Same approved result set and acceptable runtime |  | Open
Engine reads | Spark, Trino, Athena, Flink, or other production readers | No field-resolution or catalog errors |  | Open
Snapshot visibility | Current snapshot, time travel, and references | Expected snapshot and rollback behavior |  | Open
Acceptance summary
Metric | Value
Checks passed
Checks on hold
Checks failed
Overall decision

## Cutover
Cutover Planner
Choose a cutover pattern that matches the data, writer, and rollback risk.
Pattern comparison
Pattern | Sequence | Downtime | Operational burden | Rollback strength | Prerequisite | Selected?
Freeze-and-switch | Stop writers; migrate; validate; redirect; observe | Low | Low | High | Complete writer inventory and maintenance window | No
Dual-write | Backfill; write to old and new; reconcile; switch | Low | High | Medium | Stable event IDs and reconciliation process | No
Blue/green | Blue remains current; green is validated; move traffic in stages | Low | Medium | High | Separate catalog, permissions, and monitoring tests | No
Shadow rewrite | Rewrite to new table; run shadow queries; switch after acceptance | High | High | High | Storage/compute budget and reconciliation window | No
Cutover run sheet
Milestone | Value | Evidence / note
Writer freeze or dual-write start time
Validation sign-off time
Reader redirect time
Writer redirect time
Observation window ends
Source backup expiry approval
Rollback owner and contact

## Risk Register
Migration Risk Register
Keep red flags, evidence, and decisions visible to reviewers and operators.
Risk log
ID | Risk | Red flag | Evidence required | Owner / due date | Decision
R-001 | Unknown source writer | A job or manual process can still mutate the source path | Writer inventory, IAM, scheduler list |  | Hold
R-002 | Unrecoverable partitions | Non-Hive layout or inconsistent path conventions | Path inventory and source-table definition |  | Hold
R-003 | Schema identity uncertainty | Field IDs, names, or types map ambiguously | Schema report and engine compatibility tests |  | Hold
R-004 | Duplicate registration | Files may be imported more than once | File list, duplicate check, row-key test |  | Hold
R-005 | Unsafe cleanup authority | Lifecycle or operator can delete referenced files | IAM, lifecycle, retention review |  | Hold
R-006 | Validation drift | Partition or query results differ | Diff tables and checksums |  | Rollback
R-007 | Rollback not rehearsed | Team cannot restore known-good state | Rehearsal record and snapshot/backup ID |  | Hold