## Overview
Postgres CDC Failure-Injection Test Plan
Production readiness companion for failover, retries, duplicates, and sink correctness
How to use this workbook
Run each scenario in a safe environment that matches the production topology. Record evidence rather than relying on connector RUNNING status alone. Use the Test Matrix for experiments, Runbook Inputs for incident context, and Config Worksheet for version-sensitive settings.
Key operating rules
• A replay is normal when the sink commit can be ahead of the durable connector or transport checkpoint.
• PostgreSQL 17+ failover slots improve source continuity only when synchronized and ready before promotion.
• A sink must use an identity key, unique ledger, version guard, or receiver-side reconciliation appropriate to the effect.
• Never use a larger queue, offset deletion, or slot recreation as a blind fix for an unresolved correctness incident.
Workbook navigation
Test Matrix
Runbook Inputs
Config Worksheet
Scope and references
Target scope: PostgreSQL 17+ logical decoding with current Debezium PostgreSQL connector behavior. Commands, columns, configuration, and managed-service support must be checked against the exact versions and topology operated.
PostgreSQL Logical Replication Failover
PostgreSQL pg_replication_slots View
Debezium PostgreSQL Connector
Confluent Schema Evolution and Compatibility

## Test Matrix
ID | Boundary | Scenario | Setup / precondition | Fault injection | Expected source behavior | Expected delivery behavior | Sink acceptance condition | Evidence to capture | Result | Owner | Run date | Notes
CDC-01 | Source | Healthy baseline | Source, connector, transport, and sink are stable | None | Slot advances and WAL remains within the agreed horizon | No unexpected replay or backlog | Each event is applied once logically | Slot query, connector position, transport lag, sink count | Not run
CDC-02 | Connector | Crash before sink commit | A test event is available and sink consumer can be stopped | Stop consumer before sink transaction commits | Source history remains available | Event is replayed after restart | The event is eventually applied once | Timeline, source position, sink ledger, replay count | Not run
CDC-03 | Sink | Crash after sink commit | Sink transaction can be committed while checkpoint is delayed | Stop process after sink commit and before checkpoint | Source position may be replayed | Same event can be delivered again | Idempotent key prevents a second logical effect | Sink transaction log, event ID, final row/effect count | Not run
CDC-04 | Transport | Uncertain acknowledgement | Transport and consumer group are observable | Drop or delay acknowledgement at the boundary | Source continues retaining required history | Consumer retries or re-reads the event | Duplicate delivery is harmless | Producer/consumer logs and sink outcome | Not run
CDC-05 | Failover | Planned promotion with synchronized slot | Standby is current and slot synchronization is configured | Promote standby using approved procedure | Failover slot is available if readiness conditions hold | Connector route moves and may replay recent events | Sink converges without data loss | Primary/standby slot output, route test, sink reconciliation | Not run
CDC-06 | Failover | Promotion before slot is ready | Standby slot is intentionally not ready in a safe test | Promote before synchronization completes | Continuity may be unavailable or conditional | Connector cannot be assumed to resume seamlessly | Recovery decision is explicit; no blind skip | Slot state before/after, connector error, recovery action | Not run
CDC-07 | Snapshot | Snapshot overlap | Incremental or ad hoc snapshot is configured in staging | Create a change during snapshot collision window | Source keeps the change in logical history | Snapshot and streaming records can overlap | Sink deduplicates or resolves by contract | Snapshot signal, event metadata, final state | Not run
CDC-08 | Schema | Backward-incompatible change | Registry-backed converter and versioned sink are available | Introduce a deliberately incompatible schema | Source change is not enough to prove sink compatibility | Publication or sink apply may fail by policy | Failure is visible and recoverable, not silently dropped | Schema versions, compatibility result, error path | Not run
CDC-09 | Performance | Worker bottleneck | Representative load and worker metrics are available | Constrain CPU or increase serialization/transform work | WAL remains available while capture continues | Transport or sink lag grows independently | Backlog drains after bottleneck is removed | CPU, heap, queue bytes, producer latency, lag | Not run
CDC-10 | Memory | Large transaction burst | Largest realistic source transaction is known | Run the largest approved atomic transaction | Source transaction remains atomic | Connector and sink handle a burst without OOM | No silent truncation; recovery is tested | Heap, GC, queue bytes, transaction duration, restart state | Not run
CDC-11 | Ordering | Out-of-order or stale update | Two updates for one key have comparable versions | Deliver older update after newer update | Source order is recorded | Consumer receives a late or replayed update | Version/LSN guard preserves newer state | Input versions and final projection | Not run
CDC-12 | External effect | Duplicate webhook/command | Receiver supports idempotency key or reconciliation | Retry after uncertain HTTP outcome | Source event remains replayable | Effect can be retried safely | Receiver records one logical effect | Request key, receiver response, reconciliation result | Not run

## Runbook Inputs
Field | Value | Why it matters | Evidence / notes
Incident ID |  | Traceability for all evidence
Incident start (UTC) |  | Timeline anchor
Current primary |  | Promotion and route identity
Standby / candidate primary |  | Failover target
Logical slot name |  | Source continuity identity
Connector name / task |  | Offset and worker state
Offset store position |  | Checkpoint evidence
Transport topic / partition |  | Delivery ordering context
Sink target |  | Correctness boundary
Last known good event ID |  | Reconciliation anchor
Replay count |  | Delivery outcome
Duplicate count |  | Business correctness outcome
WAL pressure / headroom |  | Availability risk
Recovery owner |  | Decision authority
Closeout date |  | Incident completion

## Config Worksheet
Setting / contract | Current value | Type | Why it matters | Validation evidence | Owner
PostgreSQL version |  | Version-sensitive | Determines failover-slot workflow and available columns | Version output / change record
Debezium version |  | Version-sensitive | Connector property and restart behavior depend on version | Connector image and config export
slot.failover |  | Version-sensitive | Enables connector failover-slot behavior where documented | Config review and failover test
synchronized_standby_slots |  | Topology-sensitive | Slot synchronization is asynchronous and must be verified | Primary and standby SHOW output
max.batch.size |  | Performance | Controls records processed in a batch | Load test and lag/heap evidence
max.queue.size |  | Performance / memory | Queue bound and backpressure behavior | Queue occupancy and heap evidence
max.queue.size.in.bytes |  | Performance / memory | Byte ceiling when event sizes vary | Heap and queue-byte evidence
snapshot.fetch.size |  | Snapshot-only performance | Tune separately from streaming batch behavior | Snapshot duration and source load
Sink idempotency key |  | Correctness contract | Determines whether replay converges | Schema, constraint, and replay test
Schema Registry compatibility |  | Schema contract | Controls whether new schemas are accepted | Compatibility check and sink test
WAL recovery horizon |  | Operational SLO | Time available to recover before history is unavailable | WAL rate, disk headroom, alert test